Weeley Parish Council
Clerks Report – 20th July 2026

	
	Topic
	Action/issue
	Information
	Status

	1. 
	Reed Pond
	Initiate Management Plan
	· Obtain costs to install a chlorine pump
· Publish report on website. 
· Purchase and install Lifebuoy at pond – complete
· No progress on dredging 
	Lifebuoy now moved and flagpole erected. Flag purchased for St George’s Day..
Reed Pond to be discussed at July Meeting
Speaking to Kevin Green re work on the pond / Getting 3 quotes for next meeting
13/10 – Have second quote now but will move to later agenda as work will not start until next Spring now. Anonymous donation of £5000 received
10/2/26 – On Feb Agenda
23/2/26 – Contractor chosen just waiting for the work to start
6/7/26 – Work scheduled to start on 13th July
15/7/26 – Work complete but pond may be filled at  later date. Bin at Reed Pond raised and added as new item.

	2. 
	Investigate new Playground Equipment
	Research
	Contacted Kompan regarding a larger slide and they will site visit and give us estimates
	Will seek further quotes, but, no rush on this item.
16/7 – Possible use of funds for paths and surfacing
29/7 – to get quotes for surfacing
10/9 – One quote for surfacing received but waiting on Playdale visit and ROSPA report
13/10 – Report received deciding on next steps
16/4 – Looking into safer surfacing for the area of uneven turf. One quote received and a further one being researched.
18/5 -Attempting to get one final quote
8/6 – On June Agenda
6/7 – Need to speak to all tenders as misunderstood what we needed

	3. 
	Cloud Storage
	Find Cloud Storage for Council documents 
	Currently the Laptop is backed up to a memory card. As part of our risk assessment we should also back everything up to the cloud. This should enable document sharing.
	4/9 – Renewed Microsoft subscription which gives 1gb of storage for each of the 6 available accounts. I will begin to look at uploading most recent docs and making accessible to all.
13/11 – No progress

	4. 
	TPOs
	Keep a list of all trees in the area with TPOs
	Using TDC and Richard Ransom records collate a list of all trees within Weeley that have current TPOs listed
	6/1/26 – process started

	5. 
	9.25/5
	Finger Post at Crow Lane
	Is this listed or should it be listed. Can we just clean it or replace it. Who owns it
	22/1/26 – Clerk emailed highways Essex to clarify who owns the finger post and TDC to see if it is on a Local Heritage List
10/3- Chased Open Spaces for their permission
13/3 – Permission granted to replace – discuss on March agenda
9/4/26 – No progress
6/7/26 – Fingerpost ordered to be delivered in August

	6. 
	9.25/6
	Flashing Speed Signs
	Possibility of installing some of these in Weeley
	22/1/26 – Clerk emailed Cllr D Land to discuss

	7. 
	10/26.8
	Plaque request from WIB
	Weeley in Bloom would like to place a plaque on the bench by the Fire Station in honour of a member who used to maintain this area
	19/1 – Council voted to allow plaque
22/1 – Clerk notified WiB of permission
24/2 – Just awaiting confirmation from WIB of lettering
8/6 – Plaque seen now to arrange install
6/7/26 – Glue passed to WIB to install
21/7/26 – Plaque installed

	8. 
	11.26/8
	Barleyfields lighting
	Contact Rose and discuss the options for lighting removal
	27/2 – Spoken to Rose and sent them a Letter of Authority to speak to UK Power Networks to see what can be done with our lights.
18/5 – No update
8/6 – Chased Rose – no updates

	9. 
	Defibrillator Theft
	Defibrillator Stolen and needs to be replaced
	Report to police and insurance and then research a new Case and Defibrillator. 
	20/4 – Reported to the Police
23/4 – reported to Insurance awaiting response
8/6 – Videos sent to Insurance awaiting response
30/6 – Payment received and new defib has been purchased just awaiting install
21/7/26 – Defib installed to be added back to the circuit

	10. C
	Budgens
	Issues for residents around 7 Colchester Road
	Communicate between residents and TDC regarding ongoing issues at Colchester Road
	1/6 – Raised further issues with the Planning dept at TDC
1/7 – Decisions made on lighting.

	11. 
	02.26/11
	Goalmouths and Hedge along Old Clacton Road
	Previous goal mouths need restoring and the hedge along the road needs cutting back to allow cars to park there
	18/5 – Council agreed to Goldacre doing the work
1/6 – Advised Goldacre to do the work but hedge cutting will wait until nesting season over
6/7 – Goal mouths restored.

	12. 
	Dead Deer	
	Dead animal by St Andrews
	Dead deer at St Andrews to be removed as a hazard
	30/6 – reported to Environmental Services
1/7 – removed by Environmental services

	13. 
	Barleyfields
	Anti Social behaviour on Barleyfields
	Rose and Tendring are looking into ASB on the estate and I have requested we are copied in.
	29/6 – Contacted Rose builders so as to be kept in the conversation regarding ASB at Barleyfields.

	14. 
	Abandoned Car
	Report abandoned car in Hilltop
	Resident on FB asked about abandoned car so reported to Tending
	5/7/26 – Reported to TDC
20/7/26 – TDC reported they know the owner but have reported to DVLA as SORN but still on a public road.

	15. Broken 
	Broken bridge on Footpath
	Report to TDC
	Resident on FB complained about the bridge on Footpath 17.
	6/7/26 – Phoned TDC and reported the issue on Footpath 17
9/7/26 – TDC have added it as one for repair.
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